## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03-09/13 | 1. Determine team members and their roles, team projects, and member division of responsibility; 2. Develop project planning: project content, design architecture, technology stack used, tools used, iteration plan, and timeline; 3. Set up a development environment and become familiar with common tools and development languages; 4. Documents, forms, PPT, and videos required to complete iteration 0 | -- Solve by Providing learning resources and QA 1.Technology issue - Some of the team members are not familiar with Some technologies we gonna use, hence it is a challenge 2. We had small issue on deciding project scope and what all features we wanted to implement --solved by Commuication and Confirmation mechanism | -- Mostly solved by Commuication and Confirmation mechanism 1.Need to assign specific task to members. 2.There might be some conflicts due to time differtence 3.Some team member dont have enough knowledge on especific stacks 4.While consensus was reached at the meeting, some team members have difficulty understanding during practice. | 1.finished all team and project initial work 2.Streamline requirments 3.Detaled documents and clear ideas 4.Improved comunication and cordination among team members. | 0 | 2 | 0 | 9 | 0 | 48 | 7 | 3.5 | 12.5 | 7.5 | 7 | 5 | 3 | 6
1 | 09/14-09/21
2 | 10/01-10/14
3 | 10/15-10/28

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Yongjing Wu
Jiacheng Ding
Yueyang He
Xueqi Zhou
Rundong Zhong
Xiang Zhang

## Yongjing Wu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader, backend backup, security backup
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/11 | 12.5 | 11.5 | 1 | 0 - learn aws lambda architecture 1 - communicate and define high level requirements, 2 - lead and design the whole project architecture 5 - make project plan, send reminders to team members 6 - set up git, set up Jira 7 - research similar products, prepare presentation | 1 | 2 | 2 |  |  | 3.5 | 2 | 1 | 1. Write and review SPPP , SPPPRisk form, STD,SDD 2. Creat Team,update team introduction and create team code dir 3. Creat Jira Project and set up Sprints,Set up git, 4. Maked project plans and management plans 5. Lead and participate design whole project architure 6. Lead and Participate in Iteration 0 document writing and review | 1.Need to assign specific task to members. 2.Some team member dont have enough knowledge on especific stacks 3.While consensus was reached at the meeting, some team members have difficulty understanding during practice. | Mostly solved by Commuication and Confirmation mechanism | 0 - Learn Security test tools 1 - implement the essential requirements 2 - Completed the testing plan and realted tools 3 - Follow up on project progress and solve problems encountered by project members | 9

## Yueyang He
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/11 | 12 | 10 | 2 | 0 - Learn the basics of UI design and front-end architecture 1 - Complete the UI design of the house list, home page, personal home page, login and registration page 2 - Determine the architecture and language used in the front end (Vue, React, etc.) 4 - Communicate requirements with team members and determine the preliminary plan 5 - Submit relevant project materials0 - Learn the basics of UI design and front-end architecture | 2 | 3 | 2 | 2 | 1 |  |  |  | Completed UI design for listings, homepage, personal homepage, and login and registration pages Determined front-end architecture and language, and selected Vue/React framework Submitted project-related materials, including UI design documents and front-end architecture description Communicated requirements with team members and determined preliminary project plan | The selection of the front-end architecture took more time than expected. In the communication with team members, the requirements still need to be further clarified. | Next week, we will continue to maintain close communication with the team to clarify requirements and ensure the smooth progress of the task. Further optimize the details of UI design to ensure that the user experience and functional design are in place. | Complete the refinement of UI design, including the layout and interaction details of each page. Start coding the front-end functions to implement core functions such as login, registration, and listings. Continue to communicate requirements with team members and improve requirements documents. | 20

## Rundong Zhong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/11 | 12.5 | 9.5 | 3 | 0 - learn AWS Lambda, Cognito, S3, API Gateway, DynamoDB, GIthub Action 1 - define high level requirements. 2 - design the solution architecture for backend based on the web app functionalities and requirements 3 - implemented 3 apis for testing purpose 5 - make api development plan, send api documents to frontend team members 6 - set up git locally. 7 - research similar products, prepare presentation | 5 | 0.5 | 2 | 1 |  | 0.5 | 0.25 | 0.25 | 1. Write 2 sections of SPPP 2. write 4 sections of SDD 3. Set up git, commit a self-introduction on lab1 branch 4. Participate in Iteration 0 presentation | 1. having troubls about configuring aws IAM role configuration. 2. communication is not clear. project functionalities are not clear. | 1. spent 5 hours on configuring them and eventually set them up 2. had meeting and we discussed and double checked the requirements again | 0 - continue to learn AWS services 1 - continue to define requirements 2 - try to finish all the api requirements and documentation | 6

## Xueqi Zhou
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/11 | 13 | 11 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements 5 - Communicate with group members to determine objective, make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation and PowerPoint | 2 | 2 |  |  |  | 2 | 1 | 4 | 1. Write 3 sections of SPPP and improvement of SPPP document 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. Communication results are inaccurate and biased. 3. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again 3. Learning test tool. | 0 - continue to learn Django 1 - continue to define requirements (Detailed and iterative requirements) 3 - implement a basic hello world on Django | 6

## Jiacheng Ding
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/16 | 7.5 | 6.5 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements 4 - test 6 - git branch 7 - research similar products, prepare presentation | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0.5 | 1. Write 2 sections of SPPP 2. Write 2 sections of STD 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6.5

## Xiang Zhang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/16 | 10 | 7 | 3 | 0 - Learn Selenium 1 - Understand rental website requirements 5 - Communicate with team members, participate in meetings 6 - Set up tools for testing (Postman, Selenium) 7 - Write documentation, prepare video | 3 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | 1. Participated in meetings to understand project requirements 2. Learned Selenium and Postman for testing 3. Wrote initial documentation and prepared video for presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement ppt video | 7