## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | one or more team member drop the class | 1 | 3 | 3 | 30 | team leader and all members | 2024-09-10 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Closed
| add new team members | A person joins the team | 2 | 3 | 2 | 24 | Team leader and all members | 2024-09-14 | Quickly onboard new member | No one else joined yet | Closed
| Lack of motivation or responsibility | Team members lack motivation to complete tasks | 2 | 2 | 2 | 64 | Team leader and all members | 2024-09-14 | Have regular weekly check-ins and 1-on-1's if needed |  | Closed
Communication | duplicate work | Team members are duplicating work | 2 | 3 | 2 | 24 | Team leader and all members | 2024-09-14 | Use project management tools like GitHub KanBan or something else to avoid duplications along with regular meetings |  | Closed
| worked on wrong components | Team member worked on wrong component | 1 | 3 | 2 | 20 | Team leader | 2024-09-14 | Regular check-ins and meetings along with a project management tool to prevent that |  | Closed
| useless work | Work done that isn't useful to the project | 2 | 3 | 2 | 24 | Team leader | 2024-09-14 | Regularly review work in meetings to check for work relevance |  | Closed
| inconsistent work | Lack of standardized processes or communication leads to inconsistent quality or approaches in completing tasks. | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-14 | Establish clear guidelines, standards, and best practices for task execution and deliverable quality. Encourage regular peer reviews and feedback sessions to identify and address inconsistencies. | Communication has been sufficient to prevent this issue | Closed
Requirements | unclear requirements | Requirements for the application is not clear, leading to an application with features that's not meant to be/not be there | 2 | 3 | 2 | 24 | team leader and all members | 2024-09-14 | Talk to other teams and within the team, keep getting the latest requirements. | Have regular meetings with other teams and within the team. | Closed
| scope creep | Requirements expanded and implementation couldn't catch the requirements causing development process to fail. | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-14 | Define the requirements in the beginning of the projects and stick to the plan. | No scope creep has been an issue. | Closed
| constant requirements changes | Constant requirement change will cause wasting time on refactoring/changing the features. | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-14 | Not be too much flexiable for the requirements. | Requirements have not been changed but has had to be pared down to most essential due to time limitations. | Closed
| Overly complex requirements | Requirements that are too complex will hard to be implemented. | 2 | 1 | 3 | 60 | team leader and all members | 2024-09-14 | Don't get too complex requirements. | Requirements were kept at a level that was not overly complex. | Closed
| Unrealistic customer expactations | Unrealistic scenario expectations from the application, like too many features, user types etc. | 3 | 1 | 2 | 30 | team leader and all members | 2024-09-14 | Requirements should made clear by the user and team has to be in contact with the customer for not going too unrealistic req. | We discussed with professor and other teams and were able to reduce expectations to a reasonable feature set. | Closed
| Too many requirement | A lot of requirement will cause issues while implementing the application. | 2 | 2 | 4 | 64 | team leader and all members | 2024-09-14 | Plan to build the application. | We reduced requirements to a reasonable amount. | Closed
| Cross-functional Misalignments | Miscommunication on the feature with other teams. | 4 | 3 | 3 | 18 | team leader and all members | 2024-09-14 | Get all teams contact with each other throughout the application build. | Cross team communication was sometimes delayed and did create challenges and delays | Closed
| constant requirements changes | Constant requirement change will cause wasting time on refactoring/changing the features. | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-14 | Not be too much flexiable for the requirements. | Requirements have not been changed but has had to be pared down to most essential due to time limitations. | Closed
| Lack of Prioritization of Requirements | Having no clear priority for the requirement | 4 | 2 | 2 | 16 | team leader and all members | 2024-09-14 | Have priority for each req. | We kept an open discussion around priorities to make sure we had clear agreement on this. | Closed
| Documantation Gaps | Lack of not documenting the requirements. | 2 | 3 | 1 | 12 | team leader and all members | 2024-09-14 | Someone should be in charge of documantation and review. | We maintained and updated documentation of the requirements. | Closed
Management | improper task assignments | Tasks are assigned to team members without considering their skills, expertise, or workload, leading to inefficiencies and potential delays. | 3 | 4 | 3 | 18 | team leader | 2024-09-14 | Conduct a thorough assessment of team members' skills, expertise, and workload before assigning tasks. Match tasks to individuals based on this. Regularly review task assignments and adjust as needed. | Team meetings have been conducted to assess proper task assignments | Closed
| improper planning | Inadequate or incomplete project planning leads to uncertainties, delays, or failure to meet objectives. | 4 | 5 | 4 | 8 | team leader | 2024-09-14 | Invest sufficient time and resources upfront to conduct project planning, including defining clear objectives, scope, deliverables, timelines, and resource requirements. Regularly review and update the project plan as needed. | Planning was done but more difficulties arose than expected nevertheless | Closed
| lack of management skills | Insufficient or inexperienced management leads to ineffective decision-making, poor team coordination, and inadequate project oversight. | 3 | 4 | 4 | 24 | team leader | 2024-09-14 | Encourage open feedback and communication channels to identify and address any gaps or challenges in management skills proactively. | Team lead improved leadership skills during project development to learn how to make the most of each team member's skills and capacity | Closed
Technology competence | Not familiar with the framework used | Lack of experience with the React, potentially slowing progress and affecting quality. | 3 | 4 | 5 | 30 | All team member | 2024-09-14 | Team member search for React courses and resources. Design Leader helps other members with technical difficulties. | Team members grew their familiarity with React along the way and team members with more experience provided support. | Closed
| Not familiar with the programming language used | inexperienced with JavaScript, which could lead to inefficiencies and errors in code. | 2 | 3 | 3 | 36 | All team member | 2024-09-14 | Team member search for JavaScript courses and resources. Design Leader helps other members with technical difficulties. | Team members gained greater familiarity with JavaScript throughout the development. | Closed
| Not familiar with unit testing | Lack of knowledge in creating and executing unit tests, which are essential for verifying the functionality of individual parts of the software. | 3 | 3 | 3 | 27 | All team member | 2024-09-14 | Learn test skills from this class. QA Leader will help others with test question | Team members implemented unit tests and problem solved areas where they lacked experience. | Closed
| Not familiar with AWS | Lack of experience with the AWS, potentially causing deployment failure. | 5 | 5 | 5 | 5 | All team member | 2024-09-14 | Team member will work together and learn how to deploy on AWS by online tutorial. Ask facilitator for help when we are stuck | We switched to a lighter, more easy to use deployment option with Github. | Closed
| Not familiar with Git | Team members have limited experience using Git for version control, which is crucial for managing changes to the project codebase effectively. | 1 | 1 | 1 | 25 | All team member | 2024-09-14 | we can ask for help on discord | Some mistakes were made due to lack of experience with some aspects of Git my team members were able to resolve. | Closed
Design and implementation | Improper design | Design is not befitting of the project we are creating | 2 | 4 | 4 | 32 | Design Leader and all memeber | 2024-09-14 | Come into it with properly detailed and reliable design fully thought out | Created wireframe and distributed between members for full acess | Closed
| improper technology stack | The technology pack does not meet the requirements for the project | 2 | 4 | 4 | 32 | Design Leader and all team members | 2024-09-14 | Research tech stack needed and what would work and look best with code | We researched the technology to be used during wireframe process | Closed
| Messy code | Code that does not follow best practices for everyone to understand | 2 | 3 | 4 | 48 | All team member | 2024-09-14 | Discuss how we will be submitting and writing code before we actually code | We had discussion about how code will be handled and refactored code as we went along. | Closed
Testing | Not enough testing | Not enough testing for the applications all components and functions. | 3 | 2 | 4 | 48 | All team member | 2024-09-14 | The automation process will begin immediately. Then we'll plan to have enough testing for the whole system | Team members implemented automated tests for the features they developed.
| Depending on external systems | In our case, we're depending on other teams on most of the things. We cannot build an automated test for those functions. | 3 | 2 | 4 | 48 | All team member | 2024-09-14 | We'll be in communication with other teams the whole time. | We ran into issues with one team's service that was not caught in their testing unfortunately and caused us challenges.
| Not having a stable environment | Our application will get updated almost everyday. In that case, it's impossible to have an automated tests. | 3 | 2 | 3 | 36 | All team member | 2024-09-14 |  | The environment was stable enough to not cause major issues.
| Not having Performance Testing | Not having performance testing for our application will cause problems when there is a load on the systems. | 3 | 2 | 2 | 24 | All team member | 2024-09-14
| Not enough data for testing | We'll have different users in the system and if we don't have those users types for testing in hand, then we won't be able test those functions. | 3 | 2 | 3 | 36 | All team member | 2024-09-14 | We'll contact to other teams to create dummy data for us. | Dummy data will be used for the testings.
| Not having security testing | Not having security testing will cause security issues for the application. | 3 | 2 | 2 | 24 | All team member | 2024-09-14
| Having only manual testing | Because we're building this application in such a short time and the systems are not stable, we might have to skip automating some of the functions in the application. And this will cause insufficient testing. | 3 | 2 | 5 | 60 | All team member | 2024-09-14 | Automation will start along with manual testing. | We added automated tests while we were building the application.
Integration and deployment | Not enough time for integration and deployment | Insufficient time allocated for integrating various components and deploying the software, leading to rushed or incomplete deployment, potential errors, and operational issues. | 4 | 2 | 1 | 8 | All team member | 2024-09-14 | Allocate sufficient time in the project schedule specifically for integration and deployment activities | Access to services was delayed leaving a lot of integration work to the final iteration. Timeline for competing and deploying will be tight.
| Integration Complexity | Integrating multiple microservice and ensuring they work seamlessly with frontend components | 4 | 2 | 1 | 8 | All team member | 2024-09-14 | Start working and communicatiing with other team performing microservice as soon as possible and work on conitnuous integration | We were unable to integrate with microservices until the very end which increased risks. For one service it still worked out smoothly, the other did not resolve as well as we hoped.
| Deployment Failure | Potential issue in deploying updates or adding new features leading to service desruption. | 2 | 1 | 2 | 40 | All team member | 2024-09-14 | Keep log of the failure and work to resolve the issue.
| Security Vulnerability | Introduction of security flaws during integration or deployment that could be exploited. | 1 | 2 | 3 | 60 | Security Lead | 2024-09-14 | Access as much as security vulnerabilities the system could face before deployment and take security measures
| Service Downtime | The risk of unexpected downtime during deployment, affecting user access and system reliability. | 1 | 3 | 2 | 30 | All team member | 2024-09-14 | Debug and refactor implemetation to resolve the downtime of the service